## Agile Project Dashboard
AGILE PROJECT DASHBOARD TEMPLATE
PROJECT NAME |  | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS |  | PROJECT DELIVERABLE |  | SCOPE STATEMENT
Product Release |  | Alex B. |  |  | 20%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2026-02-02 | 2026-09-13 | 223 | Complete
| Feature 1 |  | Frank C. |  | 2026-03-06 | 2026-03-10 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2026-03-10 | 2026-09-01 | 175 | Complete
| Feature 3 |  | Jacob S. |  | 2026-03-20 | 2026-03-30 | 10 | Overdue
| Sprint 2 |  | Jacob S. |  | 2026-05-05 | 2026-08-20 | 107 | In Progress
| Feature 4 |  | Alex B. |  | 2026-05-10 | 2026-07-07 | 58 | In Progress
| Feature 5 |  | Frank C. |  | 2026-05-11 | 2026-05-20 | 9 | In Progress
| Feature 6 |  | Shari W. |  | 2026-05-11 | 2026-08-15 | 96 | Not Started
| Sprint 3 |  | Shari W. |  | 2026-11-01 | 2026-11-30 | 29 | Not Started
| Feature 7 |  | Alex B. |  | 2026-11-01 | 2026-11-05 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2026-11-05 | 2026-11-15 | 10 | Not Started
| Feature 9 |  | Jacob S. |  | 2026-11-20 | 2026-11-30 | 10 | Not Started

## BLANK - Agile Project Dashboard
AGILE PROJECT DASHBOARD TEMPLATE
PROJECT NAME |  | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS |  | PROJECT DELIVERABLE |  | SCOPE STATEMENT
0%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | [5 empty] | 0 | Complete
| Feature 1 | [5 empty] | 0 | Complete
| Feature 2 | [5 empty] | 0 | Complete
| Feature 3 | [5 empty] | 0 | Overdue
| Sprint 2 | [5 empty] | 0 | In Progress
| Feature 4 | [5 empty] | 0 | In Progress
| Feature 5 | [5 empty] | 0 | In Progress
| Feature 6 | [5 empty] | 0 | Not Started
| Sprint 3 | [5 empty] | 0 | Not Started
| Feature 7 | [5 empty] | 0 | Not Started
| Feature 8 | [5 empty] | 0 | Not Started
| Feature 9 | [5 empty] | 0 | Not Started