## Example - IT Project Dashboard
IT PROJECT DASHBOARD TEMPLATE
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/0000 | In Progress | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Planning |  | 2027-09-02 | 2027-09-03 | 2 | Complete | High |  | Not Started | High
Wireframes |  | 2027-09-03 | 2027-09-07 | 5 | Complete | Medium |  | In Progress | Medium
Image Sourcing |  | 2027-09-07 | 2027-09-12 | 6 | Complete | Low |  | Complete | Low
Graphics |  | 2027-09-09 | 2027-09-11 | 3 | Complete | Low |  | Overdue
Design |  | 2027-09-11 | 2027-09-15 | 5 | Complete | Low |  | On Hold
Search Incorporation |  | 2027-09-16 | 2027-09-17 | 2 | Overdue | High
Standards |  | 2027-09-17 | 2027-09-21 | 5 | In Progress | High
Legal |  | 2027-09-24 | 2027-10-02 | 9 | In Progress | High
Testing |  | 2027-10-02 | 2027-10-05 | 4 | In Progress | High
Optimization |  | 2027-10-05 | 2027-10-07 | 3 | On Hold | High
Platform Adaptation |  | 2027-10-06 | 2027-10-09 | 4 | Not Started | High
Launch |  | 2027-10-10 | 2027-10-10 | 1 | Not Started | Medium
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 7 | 58.33% |  | Actions | 2
Medium | 2 | 16.67% |  | Change Requests | 4
Low | 3 | 25%
TOTAL | 12 | 100%

## BLANK - IT Project Dashboard
IT PROJECT DASHBOARD TEMPLATE
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/0000 |  | 72% | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate. User to complete non-shaded cells only.
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Planning |  |  |  | 0 |  |  |  | Not Started | High
Wireframes |  |  |  | 0 |  |  |  | In Progress | Medium
Image Sourcing |  |  |  | 0 |  |  |  | Complete | Low
Graphics |  |  |  | 0 |  |  |  | Overdue
Design |  |  |  | 0 |  |  |  | On Hold
Search Incorporation |  |  |  | 0
Standards |  |  |  | 0
Legal |  |  |  | 0
Testing |  |  |  | 0
Optimization |  |  |  | 0
Platform Adaptation |  |  |  | 0
Launch |  |  |  | 0
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 |  |  | ACTUAL | 0
In Progress | 0
Complete | 0
Overdue | 0
On Hold | 0
TOTAL | 0 | 0%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*